{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":11,"n_cols":9,"rows_kept":11,"cut":false,"hidden":false,"merged":[[0,3,0,4],[2,0,3,0],[4,0,6,0],[2,1,3,1],[4,1,6,1],[2,4,3,4],[4,4,6,4],[2,5,3,5],[4,5,6,5],[2,6,3,6],[4,6,6,6],[2,7,3,7],[4,7,6,7],[2,8,3,8],[4,8,6,8]]}
["优先级","主模块","子模块","天数",null,null,null,"开始时间","完成时间"]
[1,"框架搭建","项目框架搭建",1,1,null,null,"2023-12-26","2023-12-27"]
[2,"用户模块","登录",1,3,null,null,"2023-12-28","2024-01-02"]
[null,null,"用户管理",2]
[3,"库存看板配置","新建编辑删除",3,9,null,null,"2024-01-03","2024-01-15"]
[null,null,"批量分享",3]
[null,null,"批量刷新",3]
[4,"库存看板列表","看板列表",3,3,null,null,"2024-01-16","2024-01-18"]
[5,"新老料替换","新建编辑删除",3,3,null,null,"2024-01-19","2024-01-23"]
[6,"系统配置","定时任务",2,2,null,null,"2024-01-24","2024-01-26"]
[null,"自测",null,5,5,null,null,"2024-01-29","2024-02-02"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}