{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":41,"n_cols":13,"rows_kept":41,"cut":false,"hidden":false,"merged":[[1,0,39,0],[1,1,11,1],[12,1,14,1],[16,1,20,1],[24,1,27,1],[37,1,39,1],[1,6,11,6],[12,6,14,6],[16,6,20,6],[24,6,27,6],[28,6,32,6],[11,7,15,7],[2,12,6,12],[7,12,9,12]]}
[null,"国家/归集","研发项目","备注","评审流程","当前状态","归集项目结项时间","项目计划完成时间","优先级","PM","LSD","LPI","备注"]
["超声事业部","Malus","Malus","S600 S700系列","IPD全流程","TR4","延期，需确认","暂停开发，完成送检版本发放",4,"Levi","Johnson、Jack","Irene"]
[null,null,"Malus1","S100,200，300,500等降成本项目","简化流程（上游为主的M0，TR3，TR5,TR6）","M1前",null,"S100/200:Q3\nS300/500:Q2",1,"Levi","Johnson、Jack","Irene","Selina协助完成一些任务，由Irene分配"]
[null,null,"Olive","R系列","IPD全流程","M3前",null,"Q1",1,"Irene","Johnson","Irene"]
[null,null,"Olive1","R300,500 12MLA","简化流程（上游为主的M0，TR3，TR5,TR6）","TR5前",null,"Q2(4月份）",1,"Jack","Jack","Irene"]
[null,null,"Olive2","Olive改进项目","简化流程（上游为主的M0，TR3，TR5,TR6）","TR3前",null,"Q2",2,"Irene","Johnson","Irene"]
[null,null,"Olive3","为俄罗斯改进跟换G55硬件为R700硬件","简化流程（上游为主的M0，TR3，TR5,TR6）","TR3前",null,"Q2",3,"Irene","Johnson","Irene"]
[null,null,"Verbena","D4-9EV探头","IPD全流程（探头）","TR5前",null,"Q4设计定稿",1,"Johnson","Johnson","Selina","Irene移交后协助"]
[null,null,"Tamatix","TEE探头，预研项目","NA",null,null,"Q4设计定稿",3,"James","Johnson","Selina"]
[null,null,"DAHLIA","D2-7C探头","IPD全流程（探头）","TR6",null,"Q4",3,"李文祥","李文祥","Ice"]
[null,null,"Teak","与惠泰合作ICE，VINNO注册3类主机","简化流程（上游为主的M0，TR3，TR5,TR6）",{"$nulls":4},"Johnson","Johnson","Irene"]
[null,null,"ECR","设计变更","ECO流程"]
[null,"Pista","Pista3","现有产品优化项目","ECO流程",null,"延期2024.6",null,null,"Jason","Jason ","Erika"]
[null,null,"Pista1","下一代掌超预研","NA ",{"$nulls":4},"Jason","Jason ","Erika"]
[null,null,"Pista2","第三方软件合作项目","ECO流程",{"$nulls":4},"Thomas","Thomas","Erika"]
[null,"CAMPHOR","CAMPHOR，Azolla",null,null,null,"2023.12.31关闭"]
[null,"CAMFAST","Azolla","新便携及CART预研","NA","TR0前",2025.3,null,null,"David","David","Erika"]
[null,null,"TAXUS1","V6改进项目","简化流程（上游为主的M0，TR3，TR5,TR6）",{"$nulls":4},"David","Yart","Erika"]
[null,null,"TAXUS2","V3~V5改进Cost reduction","简化流程（上游为主的M0，TR3，TR5,TR6）",{"$nulls":4},"David","Yart","Erika"]
[null,null,"CAMFAST1","V10 POC 第二阶段","ECO流程",{"$nulls":4},"Erika","James","Erika"]
[null,null,"CAMFAST2","V10质量改进","简化流程（TR3，TR5,TR6）","TR3前",null,null,null,"James","Erika","Erika"]
[null,"Galsang","Galsang","平板推车POC机型","IPD全流程","TR4前",2024.6,null,null,"Marry","David","Selina"]
[null,"Poplar","Poplar",null,null,null,"2023.12.31关闭"]
[null,"TULIP",{"$nulls":4},"2023.6已关闭"]
[null,"Cacti","Tulip G2","Tulip 192及80MHz升级","IPD全流程","TR4前",2025.9,null,null,"Andy","Alwin","May"]
[null,null,"Tulip G3","Tulip GenX4 升级,CostDown","IPD全流程","TR0 "]
[null,null,"Cactus","2D 面阵相控阵，预研项目","NA",{"$nulls":4},"Ryan","Ryan","Dora"]
[null,null,"ICE","一维ICE（可视化）","NA"]
[null,"Eucalypt1","Eucalypt1",null,"NA",null,2026.1]
[null,"Eucalypt2","Eucalypt2",null,"NA"]
[null,"Eucalypt3","Eucalypt3，OAK","软波束低成本项目","IPD全流程","M1前",null,null,null,"Alwin","Alwin","Dora"]
[null,"Eucalypt4","Eucalypt4",null,"NA"]
[null,"Eucalypt5","Eucalypt5",null,"NA"]
[null,"Lavender","Lavender","兽超9V，D10，D30~90系列","简化流程（TR3，TR5,TR6）",null,2024.12,null,null,"Serena","Serena","Selina"]
[null,"sunflower","sunflower","空化项目","NA",null,2026.12]
[null,"TEE注册（费归集项目）","TEE注册","国内注册外购的TEE探头，做3类主机注册",{"$nulls":5},"May","Alwin","May"]
[null,"软件项目（非归集项目）","1.X.X","非项目覆盖的软件更新项目","ECO流程",null,2024.12,null,null,"Jim","Jim","李豪"]
[null,null,"OEM迈微",null,"ECO流程",{"$nulls":4},"Johnson","Johnson","Irene"]
[null,null,"OEM-SonoRus&Others",null,"ECO流程",{"$nulls":4},"Johnson","Johnson","Selina"]
[null,null,"戴维医疗合作",null,"ECO流程"]
["研究院","Bread","Bread","研究院项目",null,null,"2024.12,钱没用完，需要增加子任务，是否可以添加RD1的项目归集在这个项目。可视化部门项目也挂到该项目上。"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}